## Changelog
Change log
Date (YYYY-MM-DD) | Modified By | Adjustment
2026-08-05 | EXT.Sairam Naik Gugulothu | Created
Template Version | v16

## Instruction EDI test
1 Test template document
1.1 Test template categories.
There are three categories of test templates.
Standard map test templates – these templates have a test sheet and information as well about the standard test files that are to be tested when a change is done to this map. The specific change is listed under the other test sheets in the file. These templates are placed in SharePoint under the folder for the standard map that the template belongs to.
Test template – A general test template that should be able to be used for any tests. As the test cases in UNIT /component/ UAT needs to be entered. If more thatn one map is corrected then the test cases needs to refelct this as well. This template is stored in the general EDI AD template folder at SharePoint.
Test template predefined test cases – (These templates are to be created so not in place.) Templates that has some predefined test cases where aditional ones for the specific case needs to be created. These templates are to be stored in the general EDI AD template folder at SharePoint.
1.2 Contents of the test scenario template
Change log- to be updated with creator and who has done updates.
UNIT test scenario sheet – Sheet where infomration is to be entered regarding UNIT tests.
INT Test Scenario - LW FW - Sheet where information is to be entered regarding integration tests on the Lightwell Framework.
INT Test Scenario - DSV FW - Sheet where information is to be entered regarding integration tests on the DSV Framework.
UAT Scenario – Sheet where information is to be entered regarding the UAT tests.
Issues – Here the issue list can be stored.
Test file list – List the identification of test files used. Input filename and output file name. For the standard tests there are current output files that are to be compared to the new output files, these columns might not be applicable for other tests.
Contact information- list contact information’s of persons involved in the testing.
1.3 Naming standard
The naming standard for the test document is. – Test scenario overview [RITM/EDIT]XXXX . The name is to at least be used when uploading to SharePoint. Do remember to remove the name template when using the document.
Naming of the test cases has been given a specific structure see table below.
UNI-RITM/EDIT-TEST-01A
INT-RITM/EDIT-TEST-01A
UAT-RITM/EDIT-TEST-01A
UNI = Unit
INT = Integration Test
UAT = User Acceptance Test
RGR = Regression Test
RITM = RITM number, e.g. RITM123456.
EDIT = EDI Case Task number, e.g. EDIT123456
1.4 Usage of the test cases.
There are two different ways to illustrate/write/use the test scenarios descriptions in the test document .
A) If a test fails, the issue is listed and then a retest is done and listed. And this is done until the test can be marked as ok due to passed or other considerations put it as passed.
When doing this the intention is that the naming is altered by the last character in the test name is altered in alphabetic order. If you need to continue passed Z then continue on AA, AB…
B) Only keep the success test listed. Meaning no trace of the progress to reach the green status passed. (most commonly used when creating the test document after the tests has been completed.
2 Placement in the Instruction landscape
This instruction is intended to support the usage of Test documentation part of the development procedure of EDI development. And thereby support the EDI development procedure.
2.1 Document placement on SharePoint
This document is to be placed under EDI Processes.
3 FAQ
Uploading screenshots: For changes there are on occasion in the UAT enclosed a screenshot as well showing that the result is as expected. To additional emphasise that the test has passed.
This is as well allowed to do if possible, but not mandatory as we do not always have the access to the end application. So there only the end testers confirmation will have to do.
Can the same file be used for more than one test case? Yes.
Can a test document cover several maps? Yes, but make sure to indicate what map the test case is valid for. And if it is a flow test then all mapps must work for it to pass. See Default UNIT test UNI-TEST-07A.

## UNIT Test Scenario
Test Scenarios/Scripts
Overview |  |  | Passed |  | All entries must have Tester & Test Date filled even if Status have been set to Not applicable
|  |  | Not applicable |  | to make it visible who & when made the decision
Enter RITM/EDIT-number: | EDIT0019557 |  | In verification
* indicates mandatory information |  |  | Failed
*Name | *Description of test | *Expected result | *Status | Issues/Remarks | *Tester | *Test Date (YYYY-MM-DD) | Input Filename | Output Filename | Retest | New test name | Message type | Map name/s
UNI-EDIT0019557-TEST-1DB* | Verify that SI map debugging is enabled and successfully disconnected | SI Map PTF should contain: Pre-session: object oVAR_CONNECTOR; oVAR_CONNECTOR = ""; ... oVAR_CONNECTOR = new("com.stercomm.emea.mstrombrink.dbpoolconnector.Connector"); oVAR_CONNECTOR.debugInfoMapName("[Map Name]"); oVAR_CONNECTOR.doDebug(); oVAR_CONNECTOR.connect("DSV_PARTNER_EDI_CONF"); oVAR_CONNECTOR.transactionStart(); Post-session: oVAR_CONNECTOR.disconnect(); | Not applicable |  | EXT.Sairam Naik Gugulothu | 2026-07-30 |  |  | No
UNI-EDIT0019557-TEST-01A | The test with multiple Transactions. | Output is as expected using multiple transactions | Not applicable | This is a mandatory for all the new maps. If not applicable this is to be stated. | EXT.Sairam Naik Gugulothu | 2026-07-30 |  |  | No
UNI-EDIT0019557-TEST-02A | The map is tested with single transaction | Output is as expected using single transactions | Not applicable | This is a mandatory test for all the new maps. | EXT.Sairam Naik Gugulothu | 2026-07-30 |  |  | No
UNI-EDIT0019557-TEST-03A | For the maps generating xml file as an output in the DSV FW, the encoding must be set as UTF-8. (This can be done by accessing XML file properties -> Output tab and then select UTF8 encoding from the encoding drop down list) | Output file is in UTF-8 format | Not applicable | Mandatory for all DSV FW maps with XML output | EXT.Sairam Naik Gugulothu | 2026-07-30 |  |  | No
UNI-EDIT0019557-TEST-04A | For the maps generating xml file as an output, the checkbox titled as "use character entity references instead of CDATA sections" must be checked. (This option can be found by accessing XML file properties -> output tab) | The checkbox checked. | Not applicable | Mandatory for all maps with XML output | EXT.Sairam Naik Gugulothu | 2026-07-30 |  |  | No
UNI-EDIT0019557-TEST-05A | For the maps to be used in LW FW the encoding must be set as UTF-8, including non-XML output maps | Output file is in UTF-8 format | Not applicable | Mandatory for all LW FW maps. | EXT.Sairam Naik Gugulothu | 2026-07-30 |  |  | No
UNI-EDIT0019557-TEST-06A | Perform a flow test on the Development environment for each message type being worked upon in the RITM/EDIT. | All flows are successfully translated and reach the last step of the flow (no delivery due to no connection from EDI Development). | Passed | This is mandatory for all changes to maps and flows. If not applicable, this is to be stated along with a brief explanation. | EXT.Sairam Naik Gugulothu | 2026-07-30 | 1.MBLSSTEN_20260701170132_updated.txt 2.MBLSSSYU_20260702143631_updated.txt 3.MBLSSTOD_20260629134129.txt 4.MBLSSSYO_20260701134132_updated.txt 5.45994069_DOCUMENT_MESSAGE_IN.txt 6.45994068_DOCUMENT_MESSAGE_IN.txt | 1.16100190_DOCUMENT_MESSAGE_OUT.txt 2.16100304_DOCUMENT_MESSAGE_OUT.txt 3.16100305_DOCUMENT_MESSAGE_OUT.txt 4.16100303_DOCUMENT_MESSAGE_OUT.txt 5.SSMBLZAI_20260701185812.txt 6.SSMBLNYU_20260702102030.txt | No |  | 1. ASN 2.SHIPMENTORDER 3.SHIPTO 4.SKU 5.INVENTORY BALANCE 6.RECEIPT CONFIRMATION | N/A
UNI-EDIT0019557-TEST-07A | Perform a flow test on the Development environment for each potential outcome of the Dynamic Route. | All flows are successfully translated and reach the last step of the flow (no delivery due to no connection from EDI Development). | Not applicable | This is mandatory if any setup (new or updated) involves a dynamic route, in route rules or maps, all the possible outcomes must be tested (all source and destination combinations), this includes performing regression testing on existing potential outcomes. | EXT.Sairam Naik Gugulothu | 2026-07-30 |  |  | No
UNI-EDIT0019557-TEST-08A | Perform a flow test for passthrough flows. | All flows successfully reach the last step of the flow with the correct encoding conversion(s). | Passed |  | EXT.Sairam Naik Gugulothu | 2026-07-30 | 1.MBLSSTEN_20260701170132_updated.txt 2.MBLSSSYU_20260702143631_updated.txt 3.MBLSSTOD_20260629134129.txt 4.MBLSSSYO_20260701134132_updated.txt 5.45994069_DOCUMENT_MESSAGE_IN.txt 6.45994068_DOCUMENT_MESSAGE_IN.txt | 1.16100190_DOCUMENT_MESSAGE_OUT.txt 2.16100304_DOCUMENT_MESSAGE_OUT.txt 3.16100305_DOCUMENT_MESSAGE_OUT.txt 4.16100303_DOCUMENT_MESSAGE_OUT.txt 5.SSMBLZAI_20260701185812.txt 6.SSMBLNYU_20260702102030.txt | No |  | 1. ASN 2.SHIPMENTORDER 3.SHIPTO 4.SKU 5.INVENTORY BALANCE 6.RECEIPT CONFIRMATION | N/A
UNI-EDIT0019557-TEST-09A
UNI-EDIT0019557-TEST-10A
UNI-EDIT0019557-TEST-11A
UNI-EDIT0019557-TEST-12A
UNI-EDIT0019557-TEST-13A
UNI-EDIT0019557-TEST-14A
UNI-EDIT0019557-TEST-15A
UNI-EDIT0019557-TEST-16A
UNI-EDIT0019557-TEST-17A
UNI-EDIT0019557-TEST-18A
UNI-EDIT0019557-TEST-19A

## INT Test Scenario - LW FW
Test Scenarios/Scripts
Overview |  |  | Passed
| LW Framework |  | Not tested
In verification
* indicates mandatory information |  |  | Failed
*Name | *Description of test | *Expected result | *Status | Issues/Remarks | *Tester | *Test Date (YYYY-MM-DD) | *LW Reference | *Document WFID | Retest | New test name | Message type | Map name/s
INT-EDIT0019557-TEST-01A
INT-EDIT0019557-TEST-02A
INT-EDIT0019557-TEST-03A
INT-EDIT0019557-TEST-04A
INT-EDIT0019557-TEST-05A
INT-EDIT0019557-TEST-06A
INT-EDIT0019557-TEST-07A
INT-EDIT0019557-TEST-08A
INT-EDIT0019557-TEST-09A
INT-EDIT0019557-TEST-10A
INT-EDIT0019557-TEST-11A
INT-EDIT0019557-TEST-12A
INT-EDIT0019557-TEST-13A
INT-EDIT0019557-TEST-14A
INT-EDIT0019557-TEST-15A
INT-EDIT0019557-TEST-16A
INT-EDIT0019557-TEST-17A
INT-EDIT0019557-TEST-18A
INT-EDIT0019557-TEST-19A
INT-EDIT0019557-TEST-20A

## INT Test Scenario - DSV FW
Test Scenarios/Scripts
Overview |  |  | Passed
| DSV Framework |  | Not tested
In verification
* indicates mandatory information |  |  | Failed
*Name | *Description of test | *Expected result | *Status | Issues/Remarks | *Tester | *Test Date (YYYY-MM-DD) | *Input Filename | *Output Filename | Retest | New test name | Message type | Map name/s
INT-EDIT0019557-TEST-01A
INT-EDIT0019557-TEST-02A
INT-EDIT0019557-TEST-03A
INT-EDIT0019557-TEST-04A
INT-EDIT0019557-TEST-05A
INT-EDIT0019557-TEST-06A
INT-EDIT0019557-TEST-07A
INT-EDIT0019557-TEST-08A
INT-EDIT0019557-TEST-09A
INT-EDIT0019557-TEST-10A
INT-EDIT0019557-TEST-11A
INT-EDIT0019557-TEST-12A
INT-EDIT0019557-TEST-13A
INT-EDIT0019557-TEST-14A
INT-EDIT0019557-TEST-15A
INT-EDIT0019557-TEST-16A
INT-EDIT0019557-TEST-17A
INT-EDIT0019557-TEST-18A
INT-EDIT0019557-TEST-19A
INT-EDIT0019557-TEST-20A

## UAT Scenario
Test Scenarios/Scripts
Overview |  |  | Passed
Not tested
In verification
* indicates mandatory information |  |  | Failed
*Name | *Description of test | *Expected result | *Status | Issues/Remarks | *Tester | *Test Date (YYYY-MM-DD) | *Input Filename | *Output Filename | Retest | New test name | Message type | Map name/s
UAT-EDIT0019557-TEST-01A | Text in this cell and the one below are instructions and should be deleted when creating the UAT scenarios | Text in this cell and the one below are instructions and should be deleted when creating the UAT scenarios
UAT-EDIT0019557-TEST-02A | Make sure that Description of test is specific to the change, and is describing what is being tested (and not the expected result). Make sure that there is at least one scenario covering each change made. | Make sure that Expected result is specifying what is expected outcome of the test.
UAT-EDIT0019557-TEST-03A
UAT-EDIT0019557-TEST-04A
UAT-EDIT0019557-TEST-05A
UAT-EDIT0019557-TEST-06A
UAT-EDIT0019557-TEST-07A
UAT-EDIT0019557-TEST-08A
UAT-EDIT0019557-TEST-09A
UAT-EDIT0019557-TEST-10A
UAT-EDIT0019557-TEST-11A
UAT-EDIT0019557-TEST-12A
UAT-EDIT0019557-TEST-13A
UAT-EDIT0019557-TEST-14A
UAT-EDIT0019557-TEST-15A
UAT-EDIT0019557-TEST-16A
UAT-EDIT0019557-TEST-17A
UAT-EDIT0019557-TEST-18A
UAT-EDIT0019557-TEST-19A
UAT-EDIT0019557-TEST-20A

## Regression Test Scenario
Test Scenarios/Scripts
Overview |  |  | Passed
Not tested
In verification
* indicates mandatory information |  |  | Failed
*Name | *Description of test | *Expected result | *Status | Issues/Remarks | *Tester | *Test Date (YYYY-MM-DD) | *Input Filename | *Old output Filename | *New output Filename | Retest | New test name | Message type | Map name/s
RGR-EDIT0019557-TEST-01A
RGR-EDIT0019557-TEST-02A
RGR-EDIT0019557-TEST-03A
RGR-EDIT0019557-TEST-04A
RGR-EDIT0019557-TEST-05A
RGR-EDIT0019557-TEST-06A
RGR-EDIT0019557-TEST-07A
RGR-EDIT0019557-TEST-08A
RGR-EDIT0019557-TEST-09A
RGR-EDIT0019557-TEST-10A
RGR-EDIT0019557-TEST-11A
RGR-EDIT0019557-TEST-12A
RGR-EDIT0019557-TEST-13A
RGR-EDIT0019557-TEST-14A
RGR-EDIT0019557-TEST-15A
RGR-EDIT0019557-TEST-16A
RGR-EDIT0019557-TEST-17A
RGR-EDIT0019557-TEST-18A
RGR-EDIT0019557-TEST-19A
RGR-EDIT0019557-TEST-20A

## Issues
Issue log |  |  |  | Open In progress Closed |  | Application Communication Test file Scenario Map Configuration
Issue number | Date Identified (YYYY-MM-DD) | Description | Owner | Status | Remarks | Place of failure | Date of correction
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Comments